## Master Task List
Hubitat Master Task List
Combined Hubitat items + Echos Speak carry-over tasks + Gemini 24-hour log analysis
Generation 10 |  | Item 11 completed and moved to completed section.
# | Area | Device / App | Task / Issue | Source | Status
1 | 🔊 Echos Speak | WHA / Group Dispatch | Complete WHA Group Dispatch work. One of the two tasks carried forward from the Echos Speak-specific list. | Echos Speak list | 🔴 Open — next Echos task
2 | 🖥️ Echos Speak | Echo Show | Implement/finish Echo Show Display Power support. The second carry-over task from the Echos Speak list. | Echos Speak list | 🔴 Open
3 | 🔊 Echos Speak | Device Shows / Sensors | Determine proper handling of displayBrightness as it pertains to clocks - check 'level' vs set brightness. | Echos Speak list | 🔴 Open
4 | 🌡️ Thermostat | MEM v1.8.6 / dev:510 | Fix setpoint re-entry / race condition. MEM can initiate a setpoint change and the thermostat's synchronous event can re-enter the evaluation chain before pending-write protection is established. This is the issue behind the 70° ↔ 74° bouncing. | Existing investigation | 🔴 Open — root cause identified
5 | 🌡️ Thermostat | MEM v1.8.6 | Debounce evaluatePeriods(). Gemini found the Morning transition causing the same MEM evaluation 4 times in ~1.5 sec. Add a 1–2 sec state/event buffer so the event cascade results in one evaluation. | Gemini PDF Action 3 | 🔴 Open
6 | 🌡️ Thermostat | Centralite Pearl dev:510 | Prevent redundant setpoint writes. Before issuing a heating/cooling command, compare the requested value with currentValue() and skip the command when already at the target. / Clean up duplicate thermostat logging. Eliminate command-side “Setting heatingSetpoint...” / “Setting coolingSetpoint...” messages where the resulting device event already provides the useful “was set to...” log. | Gemini PDF Action 1 / Gemini PDF Action 2 | 🔴 Open
13 | 🚶 Motion | dev:577 / dev:578 | Investigate Stairwell Motion re-arm/cooldown behavior; target approximately 30–60 seconds. | Original Hubitat list | ⬜ Open
14 | 💡 Lighting | dev:638 / app:500 | Remove redundant lighting commands being generated by the control chain. | Original Hubitat list | ⬜ Open
9 | temp/humid | temp/humid drivers | Reduce routine formatted temperature/humidity logging where appropriate. | 24-hour log evaluation | ✅ Complete
15 | 🔊 Echos Speak | app:946 / Bridge | Bridge timeout handling / quiet logging. | Echos Speak list | ✅ Complete
16 | 🔊 Echos Speak | app:946 | Legacy GUI cleanup. | Echos Speak list | ✅ Complete
17 | 🔊 Echos Speak | app:946 | Voice / Speak functionality. | Echos Speak list | ✅ Complete
18 | 🔊 Echos Speak | app:946 | Playback functionality. | Echos Speak list | ✅ Complete
19 | 🔊 Echos Speak | app:946 | Command guards. | Echos Speak list | ✅ Complete
20 | 🔊 Echos Speak | app:946 | Server log review. | Echos Speak list | ✅ Complete
16 | 🔊 Echos Speak | app:946 | W/Sensors level / capability work. | Echos Speak list | ✅ Complete
10 | 📊 AirNow AQI | dev:217 | Move polling info event to debug, change AQI updated text. | 24-hour log evaluation | ✅ Complete
11 | 🌡️ Thermostat | Advanced vThermostat / dev:1030 | Investigate stale-temperature health logic and repeated offline/online transitions. | 24-hour log evaluation | ✅ Complete
LEGEND
🔴 Open / active work |  | ⬜ Open / lower-priority item |  | ✅ Complete
Gemini PDF analysis |  | Echos Speak carry-over |  | Original Hubitat list
12 | 🩺 Device Health | dev:622 / dev:498 | Investigate/add passive device-health check-ins. | ✅ Complete | ⬜ Open
8 | 🩺 Device Health | Custom sensor drivers | Review health-check thresholds and transient offline warnings. | 24-hour log evaluation | ✅ Complete

## Summary
Hubitat Master Task List — Summary
Generation 10 — Current working inventory
Metric | Count
Total tasks | 21
Open / active | 12
Complete | 9
Original Hubitat items | 4
Echos Speak carry-over items | 9
Gemini-analysis items | 3
24-hour log-analysis items | 4