## Master Task List
Hubitat Master Task List
Combined Hubitat items + Echos Speak carry-over tasks + Gemini 24-hour log analysis
Generation 14 |  | Added 4 issues from 2026-09-25 morning log review.
# | Area | Device / App | Task / Issue | Source | Status
1 | 🔊 Echos Speak | WHA / Group Dispatch | Complete WHA Group Dispatch work. One of the two tasks carried forward from the Echos Speak-specific list. | Echos Speak list | 🔴 Open — next Echos task
2 | 🖥️ Echos Speak | Echo Show | Implement/finish Echo Show Display Power support. The second carry-over task from the Echos Speak list. | Echos Speak list | 🔴 Open
3 | 🔊 Echos Speak | Device Shows / Sensors | Determine proper handling of displayBrightness as it pertains to clocks - check 'level' vs set brightness. | Echos Speak list | 🔴 Open
8 | 🩺 Device Health | Custom sensor drivers | Review health-check thresholds and transient offline warnings. | 24-hour log evaluation | 🔴 Open
21 | 🌡️ Thermostat | MEM v1.8.10 | Investigate duplicate Morning transition and repeated Office HVAC Safety Clear execution during the 07:14 wake-up sequence. | 2026-09-25 morning log review | 🔴 Open
22 | 🛡️ Mode Manager | Mode Manager Advanced | Fix false HSM desynchronization timeout when current HSM state already matches the expected state; prevent unnecessary re-issued commands. | 2026-09-25 morning log review | 🔴 Open
23 | 🔊 Echos Speak | app:946 / Bridge | Investigate isolated speak HTTP timeout during the wake-up command burst at 07:14:52.939. | 2026-09-25 morning log review | 🔴 Open
12 | 🩺 Device Health | dev:622 / dev:498 | Investigate/add passive device-health check-ins. | Original Hubitat list | ⬜ Open
14 | 💡 Lighting | dev:638 / app:500 | Remove redundant lighting commands being generated by the control chain. | Original Hubitat list | ⬜ Open
24 | 🔊 Alexa / Hubitat | app:4 / Alexa message gateway | Investigate 07:10:15 INVALID_REQUEST_EXCEPTION / NoCorrelationSessionFound error and identify the originating action. | 2026-09-25 morning log review | ⬜ Open
4 | 🌡️ Thermostat | MEM v1.8.6 / dev:510 | Resolve MEM setpoint re-entry/race with pre-armed in-flight guards. | Existing investigation | ✅ Complete
5 | 🌡️ Thermostat | MEM v1.8.6 | Debounce MEM evaluation events to prevent duplicate period evaluations. | Gemini PDF Action 3 | ✅ Complete
6 | 🌡️ Thermostat | Centralite Pearl dev:510 | Prevent redundant setpoint writes. Before issuing a heating/cooling command, compare the requested value with currentValue() and skip the command when already at the target. / Clean up duplicate thermostat logging. Eliminate command-side “Setting heatingSetpoint...” / “Setting coolingSetpoint...” messages where the resulting device event already provides the useful “was set to...” log. | Gemini PDF Action 1 / Gemini PDF Action 2 | ✅ Complete
9 | temp/humid | temp/humid drivers | Reduce routine formatted temperature/humidity logging where appropriate. | 24-hour log evaluation | ✅ Complete
10 | 📊 AirNow AQI | dev:217 | Move polling info event to debug, change AQI updated text. | 24-hour log evaluation | ✅ Complete
11 | 🌡️ Thermostat | Advanced vThermostat / dev:1030 | Investigate stale-temperature health logic and repeated offline/online transitions. | 24-hour log evaluation | ✅ Complete
13 | 🚶 Motion | dev:577 / dev:578 | Stairwell motion re-arm/cooldown. | Original Hubitat list | ✅ Complete
15 | 🔊 Echos Speak | app:946 / Bridge | Bridge timeout handling / quiet logging. | Echos Speak list | ✅ Complete
16 | 🔊 Echos Speak | app:946 | Legacy GUI cleanup. | Echos Speak list | ✅ Complete
16 | 🔊 Echos Speak | app:946 | W/Sensors level / capability work. | Echos Speak list | ✅ Complete
17 | 🔊 Echos Speak | app:946 | Voice / Speak functionality. | Echos Speak list | ✅ Complete
18 | 🔊 Echos Speak | app:946 | Playback functionality. | Echos Speak list | ✅ Complete
19 | 🔊 Echos Speak | app:946 | Command guards. | Echos Speak list | ✅ Complete
20 | 🔊 Echos Speak | app:946 | Server log review. | Echos Speak list | ✅ Complete
LEGEND
🔴 Open / active work |  | ⬜ Open / lower-priority item |  | ✅ Complete
Gemini PDF analysis |  | Echos Speak carry-over |  | Original Hubitat list

## Summary
Hubitat Master Task List — Summary
Generation 14 — Current working inventory | 0
0
Metric | 3
Total tasks | 24
Open / active | 10
Complete | 14
Original Hubitat items | 3
Echos Speak carry-over items | 10
Gemini-analysis items | 2
24-hour log-analysis items | 8